## General Setup
6931182d2e551724a813ccdf
Productivity Matrix
Project name
Homes NSW Riverwood
Address
17-27 Hardwicke St Riverwood 2210
As of 5:49am, Tuesday 16th December
Completion 5.56%
ID | Hold | Type | Task | Task Owner | Progress
6940f00e7daa0fe87a9589bf |  |  | Project Documentation Set Up | / | / | /
6940f00e7daa0fe87a9589c3 | FALSE | Task | Estimating Handover |  | 100 | 2025-06-18
6940f00e7daa0fe87a9589c9 | FALSE | Task | Start up workshop |  | 100 | 2025-06-28
6940f00e7daa0fe87a9589cf | FALSE | Task | Project files setup on Teams |  | 100 | 2025-06-28
6940f00e7daa0fe87a9589d5 | FALSE | Task | Project files setup on Procore |  | 0 | 2025-06-28
6940f00e7daa0fe87a9589db | FALSE | Task | Dilapidation Report completed |  | 0 | 2025-06-28
6940f00e7daa0fe87a9589e1 | FALSE | Task | Dial before you dig |  | 0 | 2025-06-28
6940f00e7daa0fe87a9589e7 | FALSE | Task | Project created on Cheops |  | 0 | 2025-06-28
6940f00e7daa0fe87a9589f0 |  |  | Head Contract Items Set Up | / | / | /
6940f00e7daa0fe87a9589f4 | FALSE | Task | Bank Guarantees DRAFT copies created and issued to Homes NSW for approval |  | 0 | 2025-07-15
6940f00e7daa0fe87a9589fa | FALSE | Task | Bank Guarantees approved |  | 0 | 2025-07-20
6940f00e7daa0fe87a958a00 | FALSE | Task | Bank Guarantees generated and issued to Homes NSW Legal |  | 0 | 2025-07-25
6940f00e7daa0fe87a958a06 | FALSE | Task | Bank Guarantees received |  | 0 | 2025-07-30
6940f00e7daa0fe87a958a0c | FALSE | Task | Head Contract Deed Signed |  | 0 | 2025-08-04
6940f00e7daa0fe87a958a12 | FALSE | Task | Head Contract Copy Received |  | 0 | 2025-08-09
6940f00e7daa0fe87a958a18 | FALSE | Task | Head Contract Purchase Order (PO) received from Homes NSW |  | 0 | 2025-08-14
6940f00e7daa0fe87a958a1e | FALSE | Task | Head Contract set up on CAS - Head Contract Claims can now be made |  | 0 | 2025-08-19
6940f00e7daa0fe87a958a24 | FALSE | Task | Project Insurances |  | 0 | 2025-08-24
6940f00e7daa0fe87a958a2a | FALSE | Task | Homes NSW Contractual Documentation Submissions Completed |  | 0 | 2025-08-29
6940f00e7daa0fe87a958a30 | FALSE | Task | Head Contract Programme set up |  | 0 | 2025-09-03
6940f00e7daa0fe87a958a36 | FALSE | Task | Project Cashflow created |  | 0 | 2025-09-08
6940f00e7daa0fe87a958a3c | FALSE | Task | Construction Mgt Plan update completed |  | 0 | 2025-09-13
6940f00e7daa0fe87a958a42 | FALSE | Task | Form A1.2 - IMS Prestart Checklist |  | 0 | 2025-06-28
6940f00e7daa0fe87a958a48 | FALSE | Task | Form B1.1 - CoR Risk Register |  | 0 | 2025-06-28
6940f00e7daa0fe87a958a51 |  |  | Subcontract Items Set Up | / | / | /
6940f00e7daa0fe87a958a55 | FALSE | Task | Subcontractor Programme Set Up following finalisation of HCP |  | 0 | 2025-10-25
6940f00e7daa0fe87a958a5b | FALSE | Task | Procurement Schedule |  | 0 | 2025-11-15
6940f00e7daa0fe87a958a61 | FALSE | Task | Tender Template and Document set up |  | 0 | 2025-11-15
6940f00e7daa0fe87a958a6a |  |  | Quality Set Up | / | / | /
6940f00e7daa0fe87a958a6e | FALSE | Task | QMP Completed (QC/QA Register, inspection list etc.) |  | 0 | 2026-01-07
6940f00e7daa0fe87a958a74 | FALSE | Task | List of ITPs & Action Plans required for this project created |  | 0 | 2026-01-07
6940f00e7daa0fe87a958a7a | FALSE | Task | ITPs & Action Plan Templates created and made Project Specific |  | 0 | 2026-01-07
6940f00e7daa0fe87a958a80 | FALSE | Task | Consultant Inspection Checklist Created for COVC |  | 0 | 2026-01-22
6940f00e7daa0fe87a958a86 | FALSE | Task | COVC Crown Certifier Inspection Checklist Created |  | 0 | 2026-02-25
6940f00e7daa0fe87a958a8c | FALSE | Task | Reo Register |  | 0 | 2025-12-19
6940f00e7daa0fe87a958a92 | FALSE | Task | Concrete Register |  | 0 | 2025-12-19
6940f00e7daa0fe87a958a98 | FALSE | Task | Sample Register |  | 0 | 2025-12-19
6940f00f7daa0fe87a958a9e | FALSE | Task | Shop Drawing Register |  | 0 | 2025-12-19
6940f00f7daa0fe87a958aa7 |  |  | Project Set up | / | / | /
6940f00f7daa0fe87a958aab | FALSE | Task | CDVC1 - Receipt from PCA |  | 0 | 2025-12-19
6940f00f7daa0fe87a958ab1 | FALSE | Task | IMS implementation |  | 0 | 2026-01-05
6940f00f7daa0fe87a958ab7 | FALSE | Task | Site fencing installed |  | 0 | 2026-01-07
6940f00f7daa0fe87a958abd | FALSE | Task | Tree Protection installed |  | 0 | 2026-01-10
6940f00f7daa0fe87a958ac3 | FALSE | Task | Sediment Control installed |  | 0 | 2026-01-10
6940f00f7daa0fe87a958ac9 | FALSE | Task | Site clearing works (Removal of trees and top soil) |  | 0 | 2026-01-10
6940f00f7daa0fe87a958acf | FALSE | Task | Temp Water installed |  | 0 | 2026-01-10
6940f00f7daa0fe87a958ad5 | FALSE | Task | Temp Power installed |  | 0 | 2026-01-10
6940f00f7daa0fe87a958adb | FALSE | Task | Asbestos removal if required |  | 0 | 2026-01-10
6940f00f7daa0fe87a958ae1 | FALSE | Task | Site amenities (Site sheds & Toilets) |  | 0 | 2026-01-28
6940f00f7daa0fe87a958ae7 | FALSE | Task | Survey set up and Setout (Grid lines, Offsets & BM's) |  | 0 | 2026-01-13
6940f00f7daa0fe87a958af0 |  |  | Procurement - for CDVC1 Start | / | / | /
6940f00f7daa0fe87a958af4 | FALSE | Task | Surveying Works Package awarded |  | 0 | 2025-12-19
6940f00f7daa0fe87a958afa | FALSE | Task | Site amenities awarded |  | 0 | 2025-12-19
6940f00f7daa0fe87a958b00 | FALSE | Task | FRP Package awarded |  | 0 | 2025-12-19
6940f00f7daa0fe87a958b06 | FALSE | Task | Civil and Shoring Package awarded |  | 0 | 2025-12-19
6940f00f7daa0fe87a958b0c | FALSE | Task | Hyraulic Package awarded |  | 0 | 2025-12-19
6940f00f7daa0fe87a958b12 | FALSE | Task | Electrical & Dry Fire Package awarded |  | 0 | 2025-12-19
6940f00f7daa0fe87a958b18 | FALSE | Task | Wet Fire Package awarded |  | 0 | 2025-12-19
6940f00f7daa0fe87a958b1e | FALSE | Task | Steel Reinforcement Supply Package awarded |  | 0 | 2025-12-19
6940f00f7daa0fe87a958b24 | FALSE | Task | Concrete Supply Package awarded |  | 0 | 2025-12-19